CYFY Solutions: DATA CENTER MIGRATION – RISK ASSESSMENT

TheraNym Biologics

DATA CENTER MIGRATION – RISK ASSESSMENT

1. Executive Summary

This document outlines the risk assessment for the migration of IT and OT infrastructure. It identifies potential risks that may impact service availability, data integrity, and operational continuity, along with mitigation measures to ensure a controlled and secure migration with minimal disruption.

2. Scope Overview

The scope includes migration of IT infrastructure such as core and access switching, firewall systems, servers, wireless infrastructure, and network monitoring tools. It also includes OT rack-based networking equipment such as industrial switches, OT segmentation devices, and plant connectivity components. Supporting infrastructure such as racks, UPS systems, PDUs, structured cabling, and transport handling activities are also included within the scope.

3. Migration Assumptions

This risk assessment is based on the assumption that all configurations are backed up prior to migration, source and destination environments are fully validated and ready, required technical and operational teams are available during the migration window, and rollback mechanisms are defined and tested for critical systems.

4. Constraints & Dependencies

The migration is constrained by a defined maintenance window, physical transportation between sites, dependency on skilled resource availability during cutover, and the requirement to maintain minimal downtime for both IT and OT operations. Successful execution is also dependent on infrastructure readiness at the destination site.

5. Risk Register Summary

| Risk ID | Risk | Likelihood | Impact | Mitigation | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | Configuration loss or corruption | Medium | High | Three independent backups (SFTP, Git, offline USB) at T-7/T-3/T-1/pre-shutdown; SHA-256 manifest; lab test-restore at T-3 | CYFY Network Lead | Open |
| R2 | Hardware damage in transit | Low | High | Anti-static cartons; air-suspension climate-controlled vehicle; speed cap; escort; transit + installation insurance; cold-spare in convoy | CYFY Logistics Lead | Open |
| R3 | Connectivity failure post cut-over | Medium | High | Pre-migration LLDP/CDP reconciled at T-3; colour-coded double-ended labels; ISP smart-hands T-2; back-out plan ready before cut-over | CYFY Network Lead + ISP NOC | Open |
| R4 | Delay in restoring network services after equipment relocation | Medium | High | Verify rack installation, power, cabling, and network connectivity before bringing services online. Perform end-to-end validation and resolve issues before declaring the migration complete. | Theranym OT Operations | Open |
| R5 | Cyber-security exposure during migration | Low | High | No live uplink before config verified; firewall WAN disabled until inside legs validated; security perimeter scan at T+1h | Theranym CISO + CYFY | Open |
| R6 | Asset loss / theft in transit | Low | High | GPS-tracked vehicles; armed escort for OT; tamper-evident seals; movement register signed at every checkpoint | CYFY Logistics + Theranym Physical Security | Open |
| R7 | Destination DC not ready on schedule | Low | High | Facilities readiness gate at T-7; checklist signed jointly; defer 1 week if NO-GO | Theranym Facilities + PM | Open |
| R8 | Skill / availability gap (key engineer unavailable) | Medium | Medium | Two-deep coverage for every critical role; RACI primary + back-up; daily stand-up during migration week | CYFY Project Manager | Open |

6. Overall Risk Statement

The migration activity involves critical IT and OT infrastructure and is therefore classified as high sensitivity. Risks primarily relate to configuration integrity, network continuity, physical asset handling, and operational stability. All risks are managed through defined mitigation controls, structured validation processes, and coordinated execution planning to ensure minimal impact on business and plant operations.

7. Conclusion

The successful execution of the migration from Arro Vaccine Data Center to Borbatla Plant Data Center is dependent on strict adherence to the defined risk mitigation framework, validated technical readiness, and coordinated execution across all stakeholders. With the outlined controls in place, the migration can be executed in a controlled and secure manner with minimal operational impact.